## Risks
Project Risks
Impact | Probability (P) | Rating | Previous | Initial | Risk ID | Risk Description | Impact Description | Business Impact Value | Risk Response | Mitigation action / Last chance corrective action | Decision date dd-month-yy | Estimated cost | Provision for budget | Responsible | Related Action | Target (Plan) dd-month-yy | Done (Do) dd-month-yy | Result (Check,Act) dd-month-yy | Report
[5 empty] | 1 | Strategic/roadmap
[5 empty] | 2 | Execution/Budget
1 | qwe | #VALUE! |  |  | 2.1 | 2.1 | Project DR4 schedule slip Time to Market slippage | 1 | Adapt Project Schedule | Mitigation:Quicken finalizing the Projec Scope and set the Projec DR4 Last chance corrective action: | [5 empty] | 2019-10-31
2 | 50% | 4 | qwe |  | 2.2 | Highland – Build-2 shipment delay | AOS CD schedule slip; as least option, review and adapt the schedule |  | revise CD Schedule revise CD Schedule | Mitigation:Strictly follow and check Build-2/3 Acceptance Criteria Monitor progress closely, dig out risks and implement actions in time | [5 empty] | 2019-10-25
3 | 70% | 8.4 |  | qwe | 2.3 | 2Highland – proto units BOMs delay | Decision making on Build-2 units price delay PO/GL issuance delay |  | revise CD Schedule | Mitigation:Get BOMs ready in Agile 2 wks prior to Shipment date
1 | 60% | 2.4 |  |  | 2.4 | Highland – Build-3 shipment delay | Schedule slip |  |  | Mitigation:Strictly follow and check Build-2/3 Acceptance Criteria Monitor progress closely, dig out risks and implement actions in time
2 | 50% | 4 |  |  | 2.5 | P1 Process for SQA build | Quality of proto units to SQA & Country Specific SCC |  | revise System Test and CSC schedule. Secure Budget to replacce required number of proto units | Mitigation:Do all the necessary HW & HQA Testing guaranteeing Respin avoidance Inspect all TRs for accuracy and completeness Improve P1 Process | [5 empty] | 2019-10-25
[5 empty] | 3 | Metiers
3 |  |  |  |  | 3.1 | HW & SW resources critical | Product viability, provisionnning level |  |  | Mitigation:adapt provisionning Last chance corrective action:more resources, cost growth | [5 empty] | 2019-10-25 | 2019-10-25 | 2019-10-25 | 1